## Instructions
Workbook Instructions
The Business Case Workbook provides the toolset to develop a thorough financial analysis and justification for an information technology (IT) project. The Workbook is intended to be used in conjunction with the Business Case Template.
The Workbook comprises multiple Excel worksheets that enable input of cost estimates, quantitative benefits, and other evaluation factors. Entered data is presented in the Cost-Benefit Summary, Financial Analysis, and Selection Results worksheets.
Information within the Workbook flows from left to right. The first three worksheets after these instructions support data entry; the Financial Analysis and Cost-Benefit Summary worksheets are protected from change because they automatically summarize information from the first three worksheets. The Selection Results worksheet is not protected so the user can copy the required information into the Business Case Template.
Note: Data entry cells are in red text; complete as needed, including updating the fiscal years (FY 20xx) in the Cost_Analysis tab. Cells referenced by other worksheets are in blue text. Cells calculated or referenced within the same worksheet are in black text. Subtotal, total, and cumulative total cells are in bold black text.
An overview of the Workbook contents and line item descriptions of the worksheet elements are provided below.
Table of Contents
Cost Analysis |  | Quantifies business case cost estimates required for project development, implementation, and maintenance
Quantitative Benefit Analysis |  | Quantifies incremental cost savings, cost avoidance, and revenue generation benefits for the agency, as well as service delivery and regulatory savings for constituents
Evaluation Factors |  | Rates the qualitative and quantitative factors that support and justify an IT project, including Statutory Fulfillment, Strategic Alignment, Agency Impact Analysis, Financial Analysis, Initial Risk Consideration, and Alternatives Analysis
Cost-Benefit Summary |  | Summarizes major categories of business case costs and quantitative and qualitative benefits
Financial Analysis |  | Contains various measures of financial feasibility, including incremental and cumulative Net Cash Flow, Net Present Value (NPV), Breakeven Point, and Financial Return on Investment (ROI)
Selection Results |  | Provides a summary of project evaluation factors and financial analysis results that should be copied into the Business Case Template. Note, this worksheet is not protected.
Cost Mapping |  | Provides an estimated cost mapping from the business case costs (i.e., project costs plus non-project/operational costs) identified on the Cost Analysis worksheet to the ITD costs (i.e., project costs) and then allows agency adjustments to the ITD costs.
Agency Additional Information |  | Provides a blank, free-form spreadsheet that allows agencies to include any additional information that is helpful.
Version History |  | Summarizes the revision history of the Business Case Workbook beginning with Release 2.1 (January 2013) through Release 2.3 (September 2021).
Line Item Descriptions
Line | Category |  | Description
Cost Analysis: Business Case Cost
Project Costs (P)
P1 | Project Agency Personnel Services - Implementation |  | Project agency personnel implementation costs associated with the proposed project (Informational costs). Includes dropdown selection list.
P2 | Subtotal Project Agency Personnel-Implementation |  | Read-only summary of all project agency personnel implementation services
P3 | Project Agency Personnel Services-Maintenance |  | Project agency personnel maintenance costs associated with the proposed project
P4 | Subtotal Project Agency Personnel-Maintenance |  | Read-only summary of all project agency personnel maintenance services
P5 | Project Agency Personnel Fringe Benefits |  | Project total overhead burden for agency personnel (32.52%) including employer payroll expenses (Social Security and Medicare taxes, unemployment compensation, and workers' compensation), paid time off (holidays, sick leave, and annual leave), health insurance, retirement contributions, and longevity pay
P6 | Total Project Agency Personnel Costs |  | Read-only summary of all project agency personnel services categories
P7 | Project Non-IT Program Area Costs |  | Non-IT Program Area Costs, e.g., Staff Augmentation (Capital costs). Includes dropdown selection list.
P8 | Subtotal Program Project Non-IT Program Area Costs |  | Read-only summary of all project program area costs
P9 | IT Project Contract/Consultant Services - Implementation |  | Project implementation contract/consultant services (Capital costs). Includes dropdown selection list.
P10 | Project Subtotal Contract/Consultant-Implementation |  | Read-only summary of project implementation contract/consultant services
P11 | Project Contract/Consultant Services - Maintenance |  | Project maintenance contract/consultant services. Includes dropdown selection list.
P12 | Subtotal Project Contract/Consultant-Maintenance |  | Read-only summary of project maintenance contract/consultant services
P13 | Total Project Contract/Consultant Services Costs |  | Read-only summary of all project contract/consultant services categories
P14 | Total Project Agency and Contract Personnel Costs |  | Read-only sum of project agency Personnel Costs (P6) and Contract/Consultant Services Costs (P13)
P15 | Project - Hardware Procurement |  | All hardware procured specifically for this project. Includes dropdown selection list.
P16 | Subtotal Project Hardware Procurement |  | Read-only summary of all project hardware procurement categories
P17 | Project Maintenance - Hardware |  | All hardware maintenance and upgrades procured to support this project. Includes dropdown selection list.
P18 | Subtotal Project Hardware Maintenance |  | Read-only summary of all project hardware maintenance categories
P19 | Project Procurement - Software |  | All software procured specifically for this project. Includes dropdown selection list.
P20 | Subtotal Project Software Procurement |  | Read-only summary of all project software procurement categories
P21 | Project Maintenance - Software |  | All project software maintenance and upgrades procured to support this project. Includes dropdown selection list.
P22 | Subtotal Project Software Maintenance |  | Read-only summary of all project software maintenance categories
P23 | Total Project Hardware/Software Costs |  | Read-only summary of all project hardware and software costs
P24 | Project DCS / STS Costs |  | All DCS/STS services procured to support this project. Includes dropdown selection list.
P25 | Subtotal DCS /STS |  | Read-only summary of DCS/STS services procured to support this project
P26 | Project IV&VCosts |  | Project contract/consultant costs associated with performing IV&V services - P27(Capital) and P28 (Informational)
P27 | Project IV&V Costs |  | Summary of project contract/consultant costs associated with performing IV&V services - Capital
P28 | Project IV&V Costs |  | Summary of project contract/consultant costs associated with performing IV&V services - Informational
P29 | Subtotal IV&V |  | Ready-only project contract/consultant costs associated with performing IV&V services
P30 | Project-Other Costs |  | Other project costs to support development and implementation (captial costs). Includes dropdown list. Travel listed separately as informational cost.
P32 | Subotal Project Other Costs |  | Read-only summary of all project other costs.
P33 | Project Contingency Costs (dollar) |  | Project contingency costs if reporting dollar amount. Includes cumulative net cash flow. P27 (Capital) and P28 (Informational)
P34 | Contingency - Capital |  | Summary of project contingency costs if reporting dollar amount.
P35 | Contingency - Informational |  | Summary of project contingency costs if reporting dollar amount.
P36 | Subtotal Contingency |  | Read-only summary of contingency cost.
P37 | Total Project Hardware/Software/DCS/STS/IV&V/Other/Contingency Costs |  | Read-only summary of Project Hardware/Software/DCS/STS/IV&V/Other/Contingency costs.
Non-Project Costs (NP)
NP1 | Non-Project/Operational Agency Personnel Services |  | Non-project maintenance agency personnel costs associated with the proposed project
NP2 | Subtotal Operational Agency Personnel - Maintenance |  | Read-only summary of non-project maintenance agency personnel costs associated with the proposed project
NP3 | Operational Agency Personnel Fringe Benefits |  | Non-project total overhead burden for agency personnel (32.52%) including employer payroll expenses (Social Security and Medicare taxes, unemployment compensation, and workers' compensation), paid time off (holidays, sick leave, and annual leave), health insurance, retirement contributions, and longevity pay
NP4 | Total Non-Project/Operational Agency Personnel Costs |  | Read-only summary of all non-project personnel services categories
NP5 | Non-Project/Operational Contract/Consultant Services - Maintenance |  | Non-project/operational contract/consultant costs associated with services for ongoing operation of the proposed project, excluding hardware/software, maintenance, procurements, and other costs included under Hardware/Systems Costs
NP6 | Total Non-Project Contract/Consultant Services Costs - Maintenance |  | Read-only summary of all non-project contract/consultant maintenance services categories
NP7 | Total Non-Project/Operational Agency and Contract Personnel Costs |  | Read-only summary of non-project agency Personnel Costs and Contract/Consultant Services Costs
NP8 | Operational - Hardware/Software Maintenance |  | All non-project operational hardware/software maintenance and upgrades procured to support ongoing operations. Includes dropdown selection list.
NP9 | Subtotal Operational - Hardware/Software Maintenance |  | Read-only summary of all non-project hardware/software maintenance categories
NP10 | Operational - DCS / STS Maintenance |  | Non-project operational - DCS/STS Maintenance costs. Includes dropdown selection list.
NP11 | Subtotal Operational - DCS / STS Maintenance |  | Read-only summary of non-project operational - DCS/STS Maintenance costs.
NP12 | Operational - Other Costs |  | Non-project operational other costs. Includes dropdown selection list.
NP13 | Subtotal Operational - Other Costs |  | Read-only summary of all non-project operational other cost categories
NP14 | Total Non-Project Operational Hardware/Software/DCS/Other Costs |  | Read-only sum of all non-project hardware, software, DCS, and other costs
Project and Non-Project Total Costs
NP15 | Subtotal Non-Project Operational Costs |  | Read-only sum of Non-project Hardware/Software/DCS/Other Costs (NP14) and total Non-project agency and Contract Personnel Costs (NP7)
NP16 | Non-Project /Operational Contingency Percentage |  | Percentage used to calculate Contingency of Subtotal Non-Project Costs
NP17 | Subtotal Non-Project/Operational Costs Contingency |  | Using the Non-Project Contingency Percentage, calculation will compute % of the Subtotal Non-Project/Operational Costs (NP15) for contingencies during ongoing operations
NP18 | Total Non-Project/Operational Costs |  | Read-only sum of Non-Project Contingency (NP17) and Subtotal Non-Project/Operational Costs (NP15)
P38 | Subtotal Project Costs |  | Read-only sum of Project Hardware/Software/DCS/STS/IV&V/Other Costs (P37) less contingency (P36) and Total Project Agency and Contract Personnel Costs (P14)
P39 | Project Contingency Percentage - Capital |  | Percentage used to calculate Contingency of Subtotal Project Costs from capital costs
P40 | Project Contingency Percentage - Informational |  | Percentage used to calculate Contingency of Subtotal Project Costs from informational costs
P41 | Subtotal Project Contingency - Capital |  | Using the Project Contingency Percentage, calculation will compute % of the Subtotal Project Costs (P38) from capital costs for project contingencies during development phase
P42 | Subtotal Project Contingency - Informational |  | Using the Project Contingency Percentage, calculation will compute % of the Subtotal Project Costs (P38) from informational costs for project contingencies during development phase
P43 | Total Contingency |  | Read-only sum of all contingency categegories
P44 | Total Project Costs |  | Read-only sum of Project Contingency (P43) and Subtotal Project Costs (P38) and Program Area Costs (P8)
P45 | Total Business Case Cost |  | Read-only sum of Total Project Costs (P44) and Total Non-Project/Operational Costs (NP18)
Benefit Analysis: Quantitative Project Benefits
Agency and State Benefits
Cost Savings: Improved Efficiency/Productivity
A1 | Reduced IT and non-IT FTE costs |  | Savings from reduction of agency and contract personnel currently needed to staff the business processes and/or from a reduction in technical development and maintenance personnel needed by the agency.
A2 | Reduced IT and non-IT contractors/consultants |  | Reduction in professional services needed to support the program area and/or reduction in contract development and maintenance personnel needed by the agency
A3 | Reduced outsourced labor costs |  | Reduction in outsourcing costs
A4 | Improved workflow/business processes |  | Any reduction of program- or technology-related costs that will result from implementation of the project. Compares project costs for development and operation to savings from factors such as replacement of obsolete systems, improved efficiencies in the agency's IT infrastructure, or improved efficiencies in the agency's business processes. (Hourly Rate [see A1] x Number of employees that support business process) x Time Savings (in hours)
A5 | Reduced error rate |  | Savings related to reduced errors in reporting and processing due to error detection mechanisms in IT functionality
A6 | Reduced hardware maintenance/upgrade expense |  | Savings resulting from lower hardware acquisition, maintenance, and upgrade costs
A7 | Reduced software maintenance/upgrade expense |  | Savings resulting from lower software acquisition, maintenance, and upgrade costs
A8 | Reduced facilities rental/maintenance expense |  | Savings resulting from lower facilities acquisition, maintenance, and upgrade costs
A9 | Reduced equipment rental, supplies and materials expense |  | Savings resulting from lower equipment acquisition, maintenance, and upgrade costs and/or savings from supplies and materials
A10-A13 | Other Cost Savings (describe) |  | Any other reduction in technology- or program-related costs that will result from implementation of the project
A14 | Subtotal Cost Savings |  | Read-only sum of Cost Savings (Lines A1 through A13)
A14-1 | Reduced IT and non-IT FTE costs fringe benefits |  | Reduced IT and non-IT FTE costs fringe benefits (A1*0.3252)
A14-2 | Subtotal Fringe Savings |  | Read-only sum of Fringe Savings
Cost Avoidance: Compliance/Protection
A15 | Avoid penalties |  | Costs that may be incurred if the service provided by the project is not made available at the appropriate time, as governed by legal, government, or regulatory entities (e.g., financial penalties for not providing a federally mandated service).
A16 | Avoid loss of funding |  | Funding that may be lost if a service or program is not provided, as directed by legal, government, or regulatory entities (e.g., loss of federal matching funds).
A17 | Improved enforcement actions |  | Reduced processes to achieve enforcement outcomes based on IT functionality
A18 | Asset protection |  | Consider replacement value and likelihood of loss
A19-A22 | Other cost avoidance (describe) |  | Savings from other types of cost avoidance
A23 | Subtotal Cost Avoidance |  | Read-only sum of Cost Avoidance (Lines A15 through A22)
Revenue Generation
A24 | Additional revenue generated |  | Revenues from additional taxes, fees, permits, collections, and merchandising
A25 | Increased interest earned |  | From deposits -- federal and state
A26-A29 | Other revenue generation (describe) |  | Revenue generated from other sources
A30 | Subtotal Revenue Generation |  | Read-only sum of Revenue Generation (Lines A24 through A29)
A31 | Total Quantitative Benefits (Agency/State) |  | Read-only sum of Cost Savings (A14), Cost Avoidance (A23), and Revenue Generation (A30)
A32 | Cumulative Quantitative Benefits (Agency/State) |  | Read-only cumulative sum of Total Quantitative Benefits (Agency/State) (A31)
Benefit Analysis: Quantitative Project Benefits
Constituent (Social, Business, Environmental) Benefits
Constituent: Service Delivery Savings
C1 | Reduced constituent transaction costs |  | Reduced costs incurred by customers or clients to obtain services or products, through registering, licensing, permitting, obtaining authorizations, certifications, benefits, employment, transacting payments. Time, resources expended in traveling to government offices to apply for or obtain services; reduced customer service wait time. (Time spent initiating, checking status or other follow up with agency representative on service request.)
C2 | Reduced service delivery cycle time |  | Time elapsed from service initiation to delivery (total cycle time reduction)
C3 | Increased service availability/accessibility |  | For example, service availability increased from 40-hour work week to 24 x 7 services
C4 | Expansion of services |  | For example, access to one-stop service delivery
C5-C8 | Other service delivery improvement (describe) |  | Methods and savings that improve service delivery to constituents
C9 | Subtotal Service Delivery Savings |  | Read-only sum of Service Delivery Savings (Lines C1 through C8)
Constituent: Regulatory Savings | Constituent - Regulatory |  | Registering, licensing, permitting, obtaining authorizations, certifications, benefits, employment, transacting payments
C10 | Reduced (paper) reporting requirements |  | Registering, licensing, permitting, obtaining authorizations, certifications, benefits, employment, transacting payments
C11 | Improved ability to locate regulatory requirements |  | Reduced research time and "chasing down dead ends" due to simplified access to regulatory requirements
C12 | Improved accountability/compliance |  | Lower penalties or better accountability from IT functionality
C13 | Greater consistency in constituent/state transactions |  | Elimination of multiple communication and infrastructure for state staff due to IT functionality
C14-C17 | Other regulatory improvement (describe) |  | Methods and savings that improve constituent compliance
C18 | Subtotal Regulatory Savings |  | Read-only sum of Regulatory Savings (Lines C10 through C17)
Constituent: Other Savings | Other
C19-C23 | Other savings (describe) |  | Methods and savings that improve other service delivery to constituents
C24 | Subtotal Other Savings |  | Read-only sum of Other Savings (Lines C19 through C23)
C25 | Total Quantitative Benefits (Constituent) |  | Read-only sum of Service Delivery Savings (C9), Regulatory Savings (C18) and Other Savings (C24)
C26 | Cumulative Quantitative Benefits (Constituent) |  | Read-only cumulative sum of Total Quantitative Benefits (Constituent) (C25)
Evaluation Factors
SF | Statutory Fulfillment |  | Fulfills business mandates and strategies from federal, state, or other statutes or rules
SA | Strategic Alignment |  | Aligns with the State Strategic Plan for Information Resources Management and the agency’s strategic plan
IA | Agency Impact Analysis |  | Impacts use of IT resources at the enterprise level
FA | Financial Analysis |  | Delivers a comprehensive analysis of costs, benefits, and metrics, including Net Present Value (NPV), Breakeven Point, and ROI to the agency and state. Also includes a quantitative representation of value to the state’s constituents
RC | Initial Risk Consideration |  | Considers project risk factors and provides a preliminary review of factors that may impact the business outcome
AA | Alternatives Analysis |  | Emerges above other IT project alternatives as a result of applying a consistent method for analysis and selection
Financial Analysis
Agency/State
RA1 | Agency Benefits (Cash Inflow) |  | Equal to Total Quantitative Benefits (Agency/State) (Line A31)
RA2 | Business Case Cost (Cash Outflow) |  | Equal to Total Business Case Cost (Line P45)
RA3 | Benefit/Cost Variance (Net Cash Flow) |  | Net Cash Flow equals Total Quantitative Benefits less Total Business Case Cost (A31 minus P45)
RA4 | Cumulative Net Benefits (Cumulative Net Cash Flow) |  | Cumulative total of Benefit/Cost Variance (Net Cash Flow) (RA3)
RA5 | Net Present Value |  | Sum of the discounted (at the cost of capital) cash flows of the project. Calculated at year end as Present Value = (Future Value)/(1+interest)^n. Interest, or Discount Rate, calculated at 5%.
RA6 | Cumulative Net Present Value |  | Cumulative total of Net Present Value (RA5)
RA7 | Breakeven Point (Years 1-10) |  | Length of time required for the cumulative net benefits to equal zero
RA8 | Financial Return on Investment |  | Equal to (Agency Benefits minus Business Case Costs)/Business Case Costs (Line RA3/RA2).
Constituent
VA1 | Constituent Benefits |  | Equal to Total Quantitative Benefits (Constituent) (Line C25)
VA2 | Business Case Cost |  | Equal to Total Business Case Cost (Line P29)
VA3 | Benefit/Cost Variance |  | Total Quantitative Benefits minus Total Business Case Cost (Line C25 minus P45)
VA4 | Cumulative Net Benefits |  | Cumulative Total of Benefit/Cost Variance (VA3)
Cost Mapping
Capital Costs
P7 | Program Area Costs |  | Non-IT Program Area Costs, e.g., Staff Augmentation (Capital costs).
P13 | Total Project Contract/Consultant Services Costs (excluding Project IV&V Costs) |  | Summary of all project contract/consultant services categories
P16 | Subtotal Project Hardware Procurement |  | Summary of all project hardware procurement categories (P16)
P18 | Subtotal Project Hardware Maintenance |  | Summary of all project hardware maintenance categories (P18)
P20 | Subtotal Project Software Procurement |  | Summary of all project software procurement categories (P20)
P22 | Subtotal Project Software Maintenance |  | Summary of all project software maintenance categories (P22)
P25 | Subtotal DCS /STS |  | Summaryof all DCS/STS services procured to support this project (P25)
P27 | Project IV&V Costs |  | Summary of project contract/consultant costs associated with performing IV&V services - Capital
P32 | Subtotal Project Other Costs (excluding Project Travel Costs) |  | Summary of all project other cost categories, less project travel costs (P32)
P34 | Contingency - Capital |  | Summary of project contingency costs if reporting dollar amount.
| Other Cost |  | Other capital cost, not described above, that should be included in capital costs based on agency guidelines or project circumstances
| Other Cost |  | Other capital cost, not described above, that should be included in capital costs based on agency guidelines or project circumstances
| Other Cost |  | Other capital cost, not described above, that should be included in capital costs based on agency guidelines or project circumstances
Informational Costs (Optional)
P6 | Total Project Agency Personnel Costs |  | Summary of all project agency personnel services categories
P28 | Project IV&V Costs |  | Summary of project contract/consultant costs associated with performing IV&V services - Informational
P31 | Project Travel |  | Any project travel expenses incurred to support development and implementation
P35 | Contingency - Informational |  | Summary of project contingency costs if reporting dollar amount.
| Other Cost |  | Other informational cost, not described above, that should be included in informational costs based on agency guidelines or project circumstances
| Other Cost |  | Other informational cost, not described above, that should be included in informational costs based on agency guidelines or project circumstances
| Other Cost |  | Other informational cost, not described above, that should be included in informational costs based on agency guidelines or project circumstances
| Total ITD Project Cost |  | Read-only sum of capital and informational costs

## Cost_Analysis
Cost Analysis: Business Case Cost
Line | Category |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Total
|  |  | FY 20xx | FY 202xx | FY 20xx | FY 20xx | FY 20xx | FY 20xx | FY 20xx | FY 20xx | FY 20xx | FY 20xx
| Agency Personnel and Contractor Costs | Comment/ Method for Calculating (e.g. breakdown / description)
P1 | Informational Costs Project Agency Personnel Services - Implementation
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P2 | Subtotal Project Agency Personnel-Implementation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P3 | Project Agency Personnel Services - Maintenance
| IT Staff |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Business Staff |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P4 | Subtotal Project Agency Personnel-Maintenance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P5 | Project Agency Personnel Fringe Benefits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P6 | Total Project Agency Personnel Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P7 | Capital Costs Non-IT Program Area Costs (Staff Augmentation)
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P8 | Project Subtotal Program Area Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P9 | Capital Costs IT Project Contract/Consultant Services - Implementation
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P10 | Project Subtotal Contract/Consultant-Implementation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P11 | Project Contract/Consultant Services - Maintenance
| IT Staff |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Business Staff |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12 | Subtotal Project Contract/Consultant-Maintenance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P13 | Total Project Contract/Consultant Services Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P14 | Total Project Agency and Contract Personnel Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hardware/Software Costs
P15 | Project Procurement - Hardware
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P16 | Subtotal Project Hardware Procurement |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P17 | Project Maintenance - Hardware
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P18 | Subtotal Project Hardware Maintenance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P19 | Project Procurement - Software
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P20 | Subtotal Project Software Procurement |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P21 | Project Maintenance - Software
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P22 | Subtotal Project Software Maintenance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P23 | Total Project Hardware/Software Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P24 | Project DCS / STS Costs
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P25 | Subtotal DCS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P26 | Project IV&VCosts
P27 | IV&V - Capital |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P28 | IV&V - Informational |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P29 | Subtotal IV&V |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P30 | Project - Other Costs
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P31 | Travel - Informational |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P32 | Subotal Project Other Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P33 | Project Contingency Costs (Dollar) - Click for special instructions.
P34 | Contingency - Capital |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P35 | Contingency - Informational |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[Left Intentionally Blank]
P36 | Subtotal Contingency |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P37 | Total Project Hardware/Software/DCS/STS/IV&V/Other/Contingency Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NON-PROJECT COSTS
NP1 | Operational Agency Personnel Services - Maintenance
| IT Staff |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Business Staff |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP2 | Subtotal Operational Agency Personnel - Maintenance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP3 | Operational Agency Personnel Fringe Benefits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP4 | Total Operational Agency Personnel Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP5 | Non-Project/Operational Contract/Consultant Services - Maintenance
| IT Staff |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Business Staff |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP6 | Total Non-Project/Operational Contract/Consultant Services - Maintenance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP7 | Total Non-Project/Operational Agency and Contract Personnel Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP8 | Operational - Hardware/Software Maintenance
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP9 | Subtotal Operational - Hardware/Software Maintenance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP10 | Operational - DCS / STS Maintenance
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP11 | Subtotal Operational - DCS / STS Maintenance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP12 | Operational - Other Costs
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP13 | Subtotal Operational - Other Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP14 | Total Non-Project Operational Hardware/Software/DCS/Other Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP15 | Subtotal Non-Project Operational Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP16 | Non-Project /Operational Contingency Percentage | bar: Year 1 to Year 10
NP17 | Subtotal Non-Project/Operational Costs Contingency |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP18 | Total Non-Project/Operational Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P38 | Subtotal Project Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P39 | Project Contingency Percentage - Capital | bar: Year 1 to Year 10
P40 | Project Contingency Percentage - Informational | bar: Year 1 to Year 10
P41 | Subtotal Project Contingency - Capital |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P42 | Subtotal Project Contingency - Informational |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P43 | Total Contingency |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P44 | Total Project Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P45 | Total Business Case Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on B142: Complete this section if entering a dollar amount for contingency. If entering percentage, rows 197-198 may be applicable.
Note on B193: % must be 0 or greater.
Note on B197: If using dollar amount, see row 143.
Note on B198: If using dollar amount, see row 144.

## Quantitative_Benefit_Analysis
Benefit Analysis: Quantitative Project Benefits
Line | Category |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Total
|  |  | FY 20xx | FY 202xx | FY 20xx | FY 20xx | FY 20xx | FY 20xx | FY 20xx | FY 20xx | FY 20xx | FY 20xx
| Agency and State Benefits | Comment/ Method for Calculating
Cost Savings: Improved Efficiency / Productivity
A1 | Reduced IT and non-IT FTE costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A2 | Reduced IT and non-IT contractors/consultants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A3 | Reduced outsourced labor costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A4 | Improved workflow/business processes |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A5 | Reduced error rate |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A6 | Reduced hardware maintenance/upgrade expense |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A7 | Reduced software maintenance/upgrade expense |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A8 | Reduced facilities rental/maintenance expense |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A9 | Reduced equipment rental/supplies and materials expense |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A10 | Other cost savings (describe) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11 | Other cost savings (describe) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A12 | Other cost savings (describe) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A13 | Other cost savings (describe) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A14 | Subtotal Improved Efficiency / Productivity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A14-1 | Fringe Benefits
A14-2
A14-3 | Reduced IT and non-IT FTE costs fringe benefits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A14-4 | Subtotal Fringe Savings |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost Avoidance: Compliance / Protection
A15 | Avoid penalties |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A16 | Avoid loss of funding / loss of grant funding |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A17 | Improved enforcement actions |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A18 | Asset protection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A19 | Other cost avoidance (describe) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A20 | Other cost avoidance (describe) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A21 | Other cost avoidance (describe) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A22 | Other cost avoidance (describe) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A23 | Subtotal Cost Avoidance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Revenue Generation
A24 | Additional revenue generated |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A25 | Increased interest earned |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A26 | Other revenue generation (describe) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A27 | Other revenue generation (describe) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A28 | Other revenue generation (describe) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A29 | Other revenue generation (describe) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A30 | Subtotal Revenue Generation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A31 | Total Quantitative Benefits (Agency/State) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A32 | Cumulative Quantitative Benefits (Agency/State) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Line | Category |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Total
Constituent (Social, Business, Environmental) Benefits
Constituent: Service Delivery Savings
C1 | Reduced constituent transaction costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C2 | Reduced service delivery cycle time |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C3 | Increased service availability/accessibility |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C4 | Expansion of services |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C5 | Other service delivery improvement (describe) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C6 | Other service delivery improvement (describe) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C7 | Other service delivery improvement (describe) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C8 | Other service delivery improvement (describe) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C9 | Subtotal Service Delivery Savings |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Constituent: Regulatory Savings
C10 | Reduced (paper) reporting requirements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C11 | Improved ability to locate regulatory requirements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C12 | Improved accountability/compliance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C13 | Greater consistency in constituent/state transactions |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C14 | Other regulatory improvement (describe) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C15 | Other regulatory improvement (describe) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C16 | Other regulatory improvement (describe) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C17 | Other regulatory improvement (describe) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C18 | Subtotal Regulatory Savings |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Constituent: Other Savings
C19 | Other savings (describe) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C20 | Other savings (describe) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C21 | Other savings (describe) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C22 | Other savings (describe) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C23 | Other savings (describe) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C24 | Subtotal Other Savings |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C25 | Total Quantitative Benefits (Constituent) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C26 | Cumulative Quantitative Benefits (Constituent) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Evaluation_Factors
Evaluation Factors
The Evaluation Factors Worksheet attempts to quantify the value of intangible benefits and other factors that enable successful delivery and outcome of the project.
Score the factors below according to the following range, as applicable. Select N/A if the project does not propose to supply a value. 1 - The factor is either not present and/or of little value to the state, organization, or customer 3 - The factor is being considered and/or has moderate value to the state, organization, or customer 5 - The factor will be delivered in the project and provides high value to the state, organization, or customer Factors that are rated as "5" should be accompanied by an explanation of the reasons for rating them, and if possible, metrics by which the value can be quantified. Factors that are designated "Quantifiable" should be rated in accordance with the values produced in the Financial Analysis or other appropriate worksheet. Based on the results of initial risk consideration for the project, assign the risk factors (fifth category) according to the following range: 1 - The factor has not been considered and is not present and is therefore a risk to the project 3 - The factor is being considered, an appropriate risk response will be developed and is therefore a moderate risk impact to the project 5 - The factor has been considered and planned for, an appropriate risk response has been developed and will be managed throughout the project and is therefore a low risk to the project
Item | Factor | Rating |  |  |  |  | Explanation for Factors Rated "5"
1) Statutory Fulfillment (SF)
SF1 | The project is implemented to satisfy a direct mandate or regulation (state, federal, national, international) | N/A | N/A | 1 | 3 | 5
SF2 | The project is implemented to satisfy a derived mandate or regulation (state, federal, national, international) | N/A | N/A | 1 | 3 | 5
SF3 | Implementing the project improves the turnaround time for responses to mandates or regulatory requirements | N/A | N/A | 1 | 3 | 5
SF4 | The project results in agency compliance to mandates or regulatory requirements | N/A | N/A | 1 | 3 | 5
SF5 | The project results in agency avoidance of enforcement actions (e.g., penalties) based on mandates or regulatory requirements | N/A | N/A | 1 | 3 | 5
SF6 | Implementing the project achieves the desired intent or expected outcomes of the mandates or regulatory requirements | N/A | N/A | 1 | 3 | 5
SF7 | Implementing the project imposes stricter requirements, or different or additional requirements, than those required by the mandates or regulations | N/A | N/A | 1 | 3 | 5
|  |  | N/A | 1 | 3 | 5
| Total, Statutory Fulfillment | 0
2) Strategic Alignment (SA)
SA1 | The project is aligned with, and delivers business outcomes, that support agency and statewide goals | N/A | N/A | 1 | 3 | 5
SA2 | The project satisfies a strategic agency or state mission critical need, regardless if required by a mandate or regulation | N/A | N/A | 1 | 3 | 5
SA3 | The project results in the ability of the agency or state to better share resources with other agencies or states as part of a long-term strategic alignment effort | N/A | N/A | 1 | 3 | 5
SA4 | The project is aligned with the overall mission of the agency and state | N/A | N/A | 1 | 3 | 5
SA5 | The project strategically consolidates and streamlines business practices and administrative processes | N/A | N/A | 1 | 3 | 5
SA6 | The project is aligned with the overall vision of the agency and state | N/A | N/A | 1 | 3 | 5
SA7 | The project is aligned with the overall priorities of the agency and state | N/A | N/A | 1 | 3 | 5
SA8 | Implementing the project achieves the desired intent or expected outcomes of the agency and statewide goals | N/A | N/A | 1 | 3 | 5
SA9 | The project results in the ability of the agency or state to anticipate and respond to new business needs as part of a long-term strategic alignment effort | N/A | N/A | 1 | 3 | 5
| Total, Strategic Alignment | 0
3) Agency Impact Analysis (IA)
The project results in system(s) which:
IA1 | - support the defined architecture/standards for the agency and state | N/A | N/A | 1 | 3 | 5
IA2 | - reduce or eliminate redundant systems | N/A | N/A | 1 | 3 | 5
IA3 | - collaborate or reuse business processes or technical components from other state or federal agencies or institutions of higher learning or local governments | N/A | N/A | 1 | 3 | 5
IA4 | - improve consistency between systems within the agency through standardization | N/A | N/A | 1 | 3 | 5
IA5 | - leverage the technical capability of commercial-off-the-shelf (COTS) software packages | N/A | N/A | 1 | 3 | 5
IA6 | - define business architecture independently from technology solution, enabling the evolution of systems as new technologies emerge. | N/A | N/A | 1 | 3 | 5
IA7 | - reduce integration complexity | N/A | N/A | 1 | 3 | 5
| Total, Agency Impact Analysis | 0
4) Financial Analysis - (Agency/State and Constituent) (FA)
FA1 | Project NPV: Greater than 0 = 5; Equal to 0 = 3; Less than 0 = 1 (Quantifiable) | N/A | N/A | 1 | 3 | 5
FA2 | Project Breakeven Point (Agency/State): Years 1-3 = 5; Years 4-6 = 3; Years 7-10 (or beyond) = 1 (Quantifiable) | N/A | N/A | 1 | 3 | 5
FA3 | Project Return on Investment (Agency/State): Greater than 70% = 5; Range between 20-69% = 3; Less than 20% = 1 (Quantifiable) | N/A | N/A | 1 | 3 | 5
FA4 | Project Benefits (Constituents): Greater than project cost = 5; Equal to project cost = 3; Less than project cost = 1 (Quantifiable) | N/A | N/A | 1 | 3 | 5
FA5 | The project reduces agency staff or allows staff reassignment through efficiencies such as: - requiring fewer staff to do the work - reducing or eliminating manual processes and/or paperwork - reducing the turnaround time for business processes (Quantifiable) | N/A | N/A | 1 | 3 | 5
FA6 | The project improves/reduces the use of existing resources (hardware, software, runtime) (Quantifiable) | N/A | N/A | 1 | 3 | 5
FA7 | The project improves the agency's ability to increase collections or other revenue generation (Quantifiable) | N/A | N/A | 1 | 3 | 5
FA8 | The project results in a new service that provides additional value to a constituent or a prospective employer | N/A | N/A | 1 | 3 | 5
FA9 | The project results in a lower cost of transacting services for constituents (Quantifiable) | N/A | N/A | 1 | 3 | 5
FA10 | The project results in a service being available at more convenient times (24x7) or more locations (Quantifiable) | N/A | N/A | 1 | 3 | 5
FA11 | The project results in greater ease of use for constituents because of fewer interactions required and presentation is organized around consumer | N/A | N/A | 1 | 3 | 5
FA12 | The project results in constituents having their needs met with fewer contacts to government or fewer interactions with government employees (Quantifiable) | N/A | N/A | 1 | 3 | 5
| Total, Financial Analysis | 0
5) Initial Risk Consideration (RC)
RC1 | The executive sponsor is at the senior management level and is assigned the specific accountability for achieving all of the defined project objectives within the time and with the resources allocated |  |  | 1 | 3 | 5
RC2 | Project performance and expenditures will be measured at regular intervals against projected benefits and ROI |  |  | 1 | 3 | 5
RC3 | Oversight reviews by a senior steering committee are planned at key milestones |  |  | 1 | 3 | 5
RC4 | The project stakeholders have been identified and their expectations managed throughout the life of the project |  |  | 1 | 3 | 5
RC5 | The IT organization and technology environment are stable enough to achieve and sustain the project goals |  |  | 1 | 3 | 5
RC6 | Historical data has been reviewed to help identify the impact and probability of risk occurrence |  |  | 1 | 3 | 5
RC7 | The project roles will include verification and validation and quality assurance functions |  |  | 1 | 3 | 5
RC8 | Controls for access to sensitive information are in place |  |  | 1 | 3 | 5
RC9 | The project will not expose agency resources to untrusted users and/or networks |  |  | 1 | 3 | 5
| Total, Initial Risk Consideration | 0
6) Alternatives Analysis (AA)
AA1 | The project is supported by a comprehensive examination of alternative solutions (minimum of 3), such that, the same information set is examined for each alternative | N/A | N/A | 1 | 3 | 5
AA2 | The alternative solutions are described in detail along with the rationale for choosing or not choosing them | N/A | N/A | 1 | 3 | 5
AA3 | The analysis of alternatives summarizes the results of the agency's project cost analysis performed for each alternative and the underlying assumptions | N/A | N/A | 1 | 3 | 5
AA4 | The criteria for selecting the project is consistent with the Business Case instructions | N/A | N/A | 1 | 3 | 5
AA5 | The analysis of alternatives describes market research that was conducted to identify innovative project solutions (e.g., issued an RFI to collect information on solutions to evaluate, examined comparable initiatives implemented by other state agencies or other states) | N/A | N/A | 1 | 3 | 5
AA6 | The selected alternative, as compared with the alternatives examined, represents the best value to the state | N/A | N/A | 1 | 3 | 5
| Total, Alternatives Analysis | 0

## Goals & Obj (recommended)
[cut and paste from Businsess Case]

## Cost_Mapping
Cost Mapping - (optional worksheet) | [6 empty] | KEY: |  | Indicates values that vary from the ITD Calculation
Line | Category | Year 1 |  |  | Year 2 |  |  | Year 3 |  |  | Year 4 |  |  | Year 5 |  |  | Year 6 |  |  | Year 7 |  |  | Year 8 |  |  | Year 9 |  |  | Year 10 |  |  | Total ITD Amount Based on Project Financial Practices
|  | FY 20xx |  |  | FY 202xx |  |  | FY 20xx |  |  | FY 20xx |  |  | FY 20xx |  |  | FY 20xx |  |  | FY 20xx |  |  | FY 20xx |  |  | FY 20xx |  |  | FY 20xx
|  | ITD Calculation | ITD Amount Based on Project Financial Practices | Justification for Change | ITD Calculation | ITD Amount Based on Project Financial Practices | Justification for Change | ITD Calculation | ITD Amount Based on Project Financial Practices | Justification for Change | ITD Calculation | ITD Amount Based on Project Financial Practices | Justification for Change | ITD Calculation | ITD Amount Based on Project Financial Practices | Justification for Change | ITD Calculation | ITD Amount Based on Project Financial Practices | Justification for Change | ITD Calculation | ITD Amount Based on Project Financial Practices | Justification for Change | ITD Calculation | ITD Amount Based on Project Financial Practices | Justification for Change | ITD Calculation | ITD Amount Based on Project Financial Practices | Justification for Change | ITD Calculation | ITD Amount Based on Project Financial Practices | Justification for Change
| Capital Costs | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
P7 | Program Area Costs | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
P13 | IT Project Contract/Consultant Services Costs | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
P16 | Subtotal Project Hardware Procurement | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
P18 | Subtotal Project Hardware Maintenance | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
P20 | Subtotal Project Software Procurement | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
P22 | Subtotal Project Software Maintenance | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
P25 | Subtotal DCS/STS | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
P27 | Project IV&V Costs | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
P32 | Subtotal Project Other Costs | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
P34 | Contingency Costs (if dollar) | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
| Other (describe) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
| Other (describe) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
| Other (describe) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
| Informational Costs (Optional) | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
P6 | Total Project Agency Personnel Costs | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
P28 | Project IV&V Costs | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
P31 | Project Travel | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
P35 | Contingency Costs (if dollar) | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
| Other (describe) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
| Other (describe) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
| Other (describe) |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
| Total ITD Project Costs | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
Note on A15: less project travel costs

## Financial_Analysis
Financial Analysis
Agency/State | [6 empty] | Discount Rate | 5%
Line | Category | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 |  | Total
RA1 | Agency Benefits (Cash Inflow) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
RA2 | Business Case Cost (Cash Outflow) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
RA3 | Benefit/Cost Variance (Net Cash Flow) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
RA4 | Cumulative Net Benefits (Cumulative Net Cash Flow) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
RA5 | Net Present Value | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
RA6 | Cumulative Net Present Value | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Line | Breakeven Lookup Table | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 |  | Total
| Cumulative Net Cash Flow | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Breakeven Period Lookup | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RA7 | Breakeven Point (Years 1-10) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 0
RA8 | Financial Return on Investment | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Constituent
Line | Category | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 |  | Total
VA1 | Constituent Benefits | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
VA2 | Business Case Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
VA3 | Benefit/Cost Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
VA4 | Cumulative Net Benefits | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
VA5 | Net Present Value | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
VA6 | Cumulative Net Present Value | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Line | Breakeven Lookup Table | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 |  | Total
| Cumulative Net Cash Flow | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Breakeven Period (Years 1-10) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VA7 | Breakeven (Years 1-10) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VA8 | Statewide Value of Investment | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | #DIV/0!
| Breakeven Point | [11 empty] | 0
|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10
| Business Case Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Agency Benefits | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Net Cash Flow | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Cumulative Net Cash Flow | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10
| Business Case Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Constituent Benefits | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Flow (Variance) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cumulative Net Flow | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Business Case Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Constituent Net Flow | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Constituent Net Flow | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0

## Cost-Benefit_Summary
Summary: Project Costs
Line | Category | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Total
Project Agency Personnel and Contractor Costs
P6 | Total Project Agency Personnel Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P5 | Project Agency Personnel Fringe Benefits | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P8 | Non-IT Project Program Area Costs (Staff Augmentation) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P13 | Total Project Contract/Consultant Services Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P14 | Total Project Agency and Contract Personnel Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Hardware/Software Costs
P16 | Project Procurement - Hardware | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P18 | Project Maintenance - Hardware | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P20 | Project Procurement - Software | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P22 | Project Maintenance - Software | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P24 | DCS/STS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IV&V Project Costs
P26 | IV&V Project Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P30 | Project Other Costs
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P31 | Travel - Informational | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P37 | Total Project Hardware/Software/Other Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P38 | Subtotal Project Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P43 | Total Contingency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P44 | Total Project Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cumulative Project Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Summary: Non-Project Costs
Line | Category | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Total
Non-Project/Operational Agency Personnel and Contractor Costs
NP2 | Total Non-Project/Operational Agency Personnel Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP3 | Non-Project/Operational Agency Personnel Fringe Benefits | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP5 | Project Contract/Consultant Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP7 | Total Non-Project/Operational Agency and Contract Personnel Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non-Project Hardware/Software Costs
NP9 | Non-Project/Operational Maintenance - Hardware / Software | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP10 | Non-Project/Operational Maintenance - DCS /STS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP12 | Non-Project/Operational Other Costs
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP14 | Total Non-Project/Operational Hardware/Software/Other Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP15 | Subtotal Non-Project/Operational Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP17 | Non-Project Contingency (% of Subtotal Non-Project/Operational Costs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP18 | Total Non-Project/Operational Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cumulative Non-Project/Operational Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Summary: Quantitative Project Benefits
Line | Category | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Total
Agency and State Benefits
A14 | Cost Savings: Improved Efficiency / Productivity (including Fringe) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A23 | Cost Avoidance: Compliance / Protection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A30 | Revenue Generation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A31 | Total Quantitative Benefits (Agency/State) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A32 | Cumulative Quantitative Benefits (Agency/State) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Constituent (Social, Business, Environmental) Benefits
C9 | Constituent: Service Level Savings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C18 | Constituent: Regulatory Savings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C24 | Constituent: Other Savings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C25 | Total Quantitative Benefits (Constituent) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C26 | Cumulative Quantitative Benefits (Constituent) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Summary: Evaluation Factors
Line | Factor | Maximum Rating Possible | Rating
SF | Statutory Fulfillment | 35 | 0
SA | Strategic Alignment | 45 | 0
IA | Agency Impact Analysis | 35 | 0
FA | Financial Analysis - Government/Constituent | 60 | 0
RC | Initial Risk Consideration | 45 | 0
AA | Alternatives Analysis | 30 | 0
| Total, All Factors | 250 | 0
Note on B68: Registering, licensing, permitting, obtaining authorizations, certifications, benefits, employment, transacting payments
Note on B69: Compliance with registering, licensing, permitting, obtaining authorizations, certifications, benefits, employment, transacting payments

## Selection_Results
Selection Results
Summary: All Project Evaluation Factors
Line | Factor | Maximum Rating Possible | Rating
SF | Statutory Fulfillment | 35 | 0
SA | Strategic Alignment | 45 | 0
IA | Agency Impact Analysis | 35 | 0
FA | Financial Analysis - Government/Constituent | 60 | 0
RC | Initial Risk Consideration | 45 | 0
AA | Alternatives Analysis | 30 | 0
| Total, All Project Factors | 250 | 0
Financial Analysis: Agency/State
Line | Measure | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | 10 Year Total
RA1 | Agency Benefits (Cash Inflow) | 0 | 0 | 0 | 0 | 0 | 0
RA2 | Business Case Cost (Cash Outflow) | 0 | 0 | 0 | 0 | 0 | 0
RA3 | Benefit/Cost Variance (Net Cash Flow) | 0 | 0 | 0 | 0 | 0 | 0
RA4 | Cumulative Net Benefits (Cumulative Net Cash Flow) | 0 | 0 | 0 | 0 | 0 | 0
RA7 | Breakeven Point (Years 1 to 10) | N/A | N/A | N/A | N/A | N/A | 0
Financial Analysis: Constituents
Line | Measure | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | 10 Year Total
VA1 | Constituent Benefits | 0 | 0 | 0 | 0 | 0 | 0
VA2 | Business Case Cost | 0 | 0 | 0 | 0 | 0 | 0
VA3 | Benefit/Cost Variance | 0 | 0 | 0 | 0 | 0 | 0
VA4 | Cumulative Net Benefits | 0 | 0 | 0 | 0 | 0 | 0

## Additional_Agency_Information
Additional Agency Information - (optional worksheet)

## Lists for Dropdown (hidden)
Project Agency Personnel Services - Implementation | Capital Program Area Costs | Capital Costs Project Contract/Consultant Services - Implementation | Project - Hardware Procurement | Project Maintenance - Hardware | Project Procurement - Software | Project Maintenance - Software | DCS / STS Costs | Project - Other Costs | Non-Project/Operational Maintenance - Hardware/Software | Operational Other
Project Management/Administration | Project Manager | Project Management/Administration | Hardware - Mainframe | Hardware - Mainframe | Software - Mainframe | Software - Mainframe | DCS - Texas Private Cloud | Project Data Communications | Hardware - Mainframe | Operational Data Communications
Policy and Procedures | Business Analyst | Policy and Procedures | Hardware - Unix Server | Hardware - Unix Server | Software - Unix Server | Software - Unix Server | DCS - Public Cloud Manager | Project Voice Communications | Hardware - Unix Server | Operational Voice Communications
Requirements | Development | Requirements | Hardware - Intel Server | Hardware - Intel Server | Software - Intel Server | Software - Intel Server | DCS - Mainframe Services | Project Equipment Rental/Supplies and Materials | Hardware - Intel Server | Operational Equipment Rental/Supplies and Materials
Design | Trainer | Design | Hardware - Storage | Hardware - Storage | Software - Storage | Software - Storage | DCS - Technology Solution Services | Project Facilities Rental/Maintenance Expenses | Hardware - Storage | Operational Facilities Rental/Maintenance Expenses
Development/Programming | Other (describe) | Development/Programming | Hardware - Desktop | Hardware - Desktop | Software - Desktop | Software - Desktop | DCS - Print, Mail, & Digitization | Project Disaster Recovery | Hardware - Desktop | Operational Disaster Recovery
System Test |  | System Test | Hardware - Network | Hardware - Network | Software - Network | Software - Network | Texas.gov - Constituent Payment Portal | Project Other Cost (describe) | Hardware - Network | Operational Travel
Training |  | Training | Hardware - Other (describe) | Hardware - Other (describe) | Software - Other (describe) | Software - Other (describe) | Texas.gov - Texas by Texas Digital Assistant |  | Hardware - Other (describe) | Non-Project Other Cost (describe)
Conversion |  | Conversion |  |  |  |  | Texas.gov - Identity Solutions |  | Software - Mainframe
Implementation |  | Implementation |  |  |  |  | Managed Security Services - Device Monitoring |  | Software - Unix Server
Database Administration |  | Database Administration |  |  |  |  | Managed Security Services - Incident Response |  | Software - Intel Server
System Operations |  | System Operations |  |  |  |  | Managed Security Services - Assessments |  | Software - Storage
Technical Support |  | Technical Support |  |  |  |  | Open Data Portal |  | Software - Desktop
Documentation |  | Documentation |  |  |  |  | Other - Describe |  | Software - Network
Help Desk Personnel |  | Help Desk Personnel | [6 empty] | Software - Other (describe)
Agile Certified Practioner |  | Network Administration
Agile Integrator |  | IV&V Costs
Agile Developer |  | Warranty/Maintenance Period
Scrum Master |  | Agile Certified Practioner
Other (describe) |  | Agile Integrator
Agile Developer
Scrum Master
Other (describe)

## Version History
Version History
Version | Date | Description
2.4 | 2023-08-09 | Removed extraneous agency text; updated Instructions tab for filling in Fiscal Year info on Cost_Analysis tab; updated Cost_Analysis tab FYs (row 3).
2.3 | 2021-09-01 | Version 2.3 Released. Instructions, Cost Analysis, Quantitative Benefit Analysis, and Cost Mapping worksheets updated.
2.2 | 2013-08-31 | Version 2.2 Released. Business Case Workbook updated with the addition of the Version History worksheet.
2.1 | 2013-01-28 | Version 2.1 Released. Business Case Workbook updated to use FY2014-2015 agency personnel fringe benefits percentage calculation set by the Legislative Budget Board to 29.74% (Social Security 6.5%, ERS Retirement 7.65%, ERS Health Insurance 15.59%).
2.0 | 2012-07-10 | Version 2.0 Released. The version history detail for Business Case Workbook 2.0 and earlier releases are recorded in the Business Case Instructions.